## Agile Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1 | 8
Task |  |  | Done | 7 | 5 | 3 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 1 | 5 | 0 | 1 | 0
Task |  |  |  | 1 | 0.5 | 0 | 3 | 0 | 0 | 0
Task |  |  |  | 0.5 | 1 | 2 | 3 | 1 | 0 | 0
User Story #2 | 1
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 | 0 | 1
User Story #3 | 5
Task |  |  |  | 8 | 6 | 0 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 | 0 | 3
User Story #4 | 8
Task |  |  |  | 9 | 4 | 2 | 2 | 1 | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
User Story #5 | 3
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 1
TOTAL |  |  |  | 78 | 60 | 59 | 41 | 20 | 18 | 14
CLICK HERE TO CREATE IN SMARTSHEET

## Sprint Backlog -1
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
Database design (Prototype) | 2
Analyse possible tables |  | Uttam Tamang, Ashish Pokhrel | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 1
Database Design (API Based) | 4
Setup necessary frameworks and Configurations |  | Uttam Tamang, Ashish Pokhrel | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0
Create necessary Schemas |  | Uttam Tamang, Ashish Pokhrel | Completed | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 1
Develop Useful routes |  | Uttam Tamang, Ashish Pokhrel | Completed | 2 | 0 | 0 | 1 | 1 | 1 | 1
Secure and check routes with testing tools |  | Uttam Tamang, Ashish Pokhrel | Completed | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 2
Login and Registration System (UI) | 2
Design Login and Registration Interface |  | Daisyna Shrestha | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 1
Integrate Userinterface with developed Api |  | Daisyna Shrestha, Uttam Tamang | Completed | 1 | 0 | 0 | 0 | 1 | 0 | 0
Forgot your password | 2
Research upon references |  | Ashish Pokhrel | On progress | 1 | 0 | 0 | 0 | 0 | 0 | 0
Implement on the system |  | Ashish Pokhrel | On progress | 1 | 0 | 0 | 0 | 0 | 0 | 0
Sprient testing / review | 3
Validation Testing |  | Asmita Adhikari, Anupama Malla | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 1
Unit Testing |  | Asmita Adhikari, Anupama Malla, Sadina Magar | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 1
Blackbox testing |  | Asmita Adhikari, Anupama Malla | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 1
TOTAL |  |  |  | 14 | 3.5 | 0.5 | 1 | 2.5 | 1.5 | 9

## Sprient Backlog-2
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
Design Admin User Interface
Analyse necessary reference designs |  | Uttam Tamang | On Progress | 2 | 2 | 0 | 0 | 0 | 0 | completed for sprint1. successfully
Develop Interface |  | Uttam Tamang | On Progress
Add and Delete Products
Design UI form inorder to insert products |  | Daisyna Shrestha | Completed | 4 | 0.5 | 2 | 2 | 0 | 0
Integrate UI with API |  | Daisyna Shrestha, Ashish Pokhrel | Completed | 3 | 2 | 1 | 1
Create necessary functions and integrate in UI components |  | Daisyna Shrestha, Ashish Pokhrel | Completed | 3 | 2 | 1 | 1
Update Products
Design UI design for update Products |  | Daisyna Shrestha, Ashish Pokhrel | Completed
Integrate API and necessary functions in UI components |  | Daisyna Shrestha, Ashish Pokhrel | Completed
Sprient testing / review
Validation Testing |  | Asmita Adhikari, Anupama Malla | Completed
Unit Testing |  | Asmita Adhikari, Anupama Malla, Sadina Magar | Completed
Blackbox testing |  | Asmita Adhikari, Anupama Malla | Completed
TOTAL |  |  |  | 12 | 6.5 | 4 | 4 | 0 | 0 | 0

## Sprint Backlog-3
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
View Product Details | 2
Design Ui for displaying product's informations |  | Daisyna Shrestha | On Progress | 2 | 2 | 0 | 0 | 0 | 0 | completed for sprint1. successfully
Integrate API and click events in UI components |  | Uttam Tamang, Daisyna Shrestha | On Progress
Search Products | 2
Design UI form inorder to Search products |  | Daisyna Shrestha | Done | 4 | 0.5 | 2 | 2 | 0 | 0
Integrate UI with API |  | Uttam Tamang | Done | 3 | 2 | 1 | 1
Create necessary functions and integrate in UI components |  | Uttam Tamang | Done | 3 | 2 | 1 | 1
Sort and Filter products | 2
Design necessary functions and integrate API |  | Uttam Tamang | Done
Assign those functions to UI components |  | Uttam Tamang | Done
Sprient testing / review | 3
Validation Testing |  | Asmita Adhikari, Anupama Malla | Done
Unit Testing |  | Asmita Adhikari, Anupama Malla, Sadina Magar | Done
Blackbox testing |  | Asmita Adhikari, Anupama Malla, Sadina Magar | Done
TOTAL |  |  |  | 12 | 6.5 | 4 | 4 | 0 | 0 | 0

## Sprint Backlog-4
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
Add Product into Cart | 2
Design Cart Ui |  | Daisyna Shrestha | Done | 2 | 2 | 0 | 0 | 0 | 0 | completed for sprint1. successfully
Integrate API and click events in UI components |  | Uttam Tamang, Daisyna Shrestha | Done
Edit Product quantities in the cart | 2
Research on necessary references for QTY feature |  | Uttam Tamang, Ashish Pokhrel | Done | 4 | 0.5 | 2 | 2 | 0 | 0
Design working QTY UI element |  | Uttam Tamang, Ashish Pokhrel | Done | 3 | 2 | 1 | 1
Create necessary functions and integrate in UI components |  | Uttam Tamang | Done | 3 | 2 | 1 | 1
Remove Products from the cart | 2
Design necessary functions and integrate API |  | Uttam Tamang | Done
Assign those functions to UI components |  | Uttam Tamang | Done
Order Product from cart
Create suitable Button and implement order function in Button UI |  | Uttam Tamang, Ashish Pokhrel, Daisyna Shrestha | Not Done
Sprient testing / review
Validation Testing |  | Asmita Adhikari, Anupama Malla | Done
Unit Testing |  | Asmita Adhikari, Anupama Malla, Sadina Magar | Done
Blackbox testing |  | Asmita Adhikari, Anupama Malla, Sadina Magar | Done
TOTAL |  |  |  | 12 | 6.5 | 4 | 4 | 0 | 0 | 0

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.